## Work Plan by Date Template
[FOA Title] Work Plan by Date
DATE | TASK/SECTION | LEAD | STATUS/NOTES
Month
Month
Month

## Work Plan Sample
Proposal Work Plan by Date
DATE | TASK/SECTION | LEAD | STATUS/NOTES
August
23 | Applicant Information Webinar 11am Pacific Time |  | Viewed by: Bill, Carol, Cindy
28 | PI/Admin planning meeting | Bill/Cindy
Sept.
2 | NCSU Holiday
9 | Budget development: begins | Barbara
| Key Personnel - Co-PD/PIs, Co-Invs: Confirmed | PD/PIs
11 | Biosketches: Solicit | Cindy | Solicited by Cindy 10/11
| Confirmed: List of Subcontracts and documents needed | Team
13 | Proposal Kick-Off Meeting | Team
16 | Technical Draft v1: due and delivered to reviewers | PD/PIs
| Letters of Support: Anticipated list confirmed | Team
18 | Letters of Support: Solicit | Cindy | Solicited by Cindy 10/16
| Subcontract Deliverables: Solicit | Cindy | Solicited by Cindy 10/18
| Facilities/resources: Solicit from Co-Is & partners | Cindy | Soliceted by Cindy 10/18
| Technical Draft v1: comments returned | Reviewers
20 | Biosketches: Due | Cindy | 10/21: Received from: Carol, Mike, Todd Outstanding: Mike
27 | NIH Conference Call 10AM Pacific Time |  | Attended by: Bill
Oct.
9 | Subcontract Deliverables (draft): Due | Cindy
Letters of Support: Due
10 | Budget v1 (Prime+Subs): Due | Barbara
13 | Letter of Intent: due | PD/PIs | Sumitted 9/15
16 | Technical Draft v2: due and delivered to reviewers | PD/PIs
| Budget, Justification and Appendicies v2: Due | Barbara
| Subcontract Deliverables (final): Due | Cindy
21 | Technical Draft v2: comments returned | PD/PIs
23 | Budget and Justification: due | Barbara
| SF424 app package: due | Barbara
28 | Route eGC1 | Barbara | Final budget, budget justification, SF424 app package, draft science
30 | Technical Draft v3: due and delivered to reviewers | PI/PDs
Nov.
1 | Approved eGC1: due to OSP
4 | Technical Draft v4 (Final): complete | PD/PIs
5 | Copy editing and proofreading: complete | Cindy | PI accepts/rejects copy edits
6 | Production: PDFing and ready to submit | Cindy | PDFing complete, then PI does final review of hard copy (entire doc)
7 | Due to OSP: All elements "Ready To Submit" | Bill/Barabra
11 | NCSU Holiday
13 | Due to Sponsor | OSP
| Email NIA Referral Office once submitted | Cindy
14 | Celebrate!